## Apply
Build Quality
Iteration | Build Quality | Functional Bugs | UI Bugs | Validation Bugs | Integration/Enviro/Config
17th Nov'15 - 30th Nov'15 | 90 | 3 | 2 | 0 | 0
01stDec'15 -14thDec'15 | 75.66 | 9 | 1 | 0 | 0
15th Dec'15 - 28th Dec'15 | 91 | 1 | 5 | 0 | 0
29thDec'15-11thJan'16 | 73.33 | 13 | 1 | 0 | 0
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov'15 - 30th Nov'15 | 8 | 4 | 4 | 0 | 4
01stDec'15 -14thDec'15 | 9 | 0 | 3 | 1 | 5
15th Dec'15 - 28th Dec'15 | 6 | 2 | 2 | 0 | 4
29thDec'15-11thJan'16 | 8 | 5 | 3 | 2 | 3
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov'15 - 30th Nov'15 | 2 | 1 | 1
1st Dec'15 - 14th Dec'15 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0 | 0 | 0
29thDec'15-11thJan'16 | 0 | 0 | 0
No Bug logged

## Resdex
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 90.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## MNR
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## CSMRequirement
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## CSMApplication
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## JobPosting
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## RESMNJ
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA

## JobSearch
Build Quality
Iteration | Build Quality | Functional Bugs | Integration/Enviro/Config | UI | Incomplete requirement | Insufficient Impact Analysis | Implicit
17th Nov'15-30th Nov'15 | 39.09 | 6 | 1 | 3 | 1 | 1 | 0
1st Dec'15 - 14th Dec'15 | 87.2 | 4 | 0 | 0 | 0 | 0 | 0
15th Dec'15 - 28th Dec'15 | 0.71 | 4 | 0 | 0 | 1 | 0 | 1
29thDec'15-11thJan'16 | 95 | 3 | 0 | 0 | 0 | 0 | 0
NIR-102 | 84.4737 | 1 | 0 | 2 | 0 | 1 | 2
Functional Automation Coverage
Status | Total Stories | Automatable | Automated | Not Automated | Not Automatable
17th Nov-30th Nov'15 | 10 | 8 | 8 | 0 | 2
1st Dec'15 - 14th Dec'15 | 13 | 5 | 5 | 0 | 8
15th Dec'15 - 28th Dec'15 | 12 | 3 | 3 | 0 | 9
29thDec'15-11thJan'16 | 10 | 6 | 6 | 0 | 4
NIR-102 | 14 | 5 | 5 | 0 | 9
| Live issues (Except client issues) | Client Reported Issues (Code Fixes) | Client Reported Issues (Data Fixes)
17th Nov-30th Nov'15 | 0 | 0 | 2
1st Dec'15 - 14th Dec'15 | 0 | 0 | 1
15th Dec'15 - 28th Dec'15 | 0 | 0 | 1
29thDec'15-11thJan'16 | 0 | 1 | 3
NIR-102 | 2 | 1 | 2
Naukri India Resdex
Total Bugs | Open | 1
| Closed | 3
P1 | SLA Met | 3
| SLA Not Met | 1
P2 | SLA Met | 0
| SLA Not Met | 0
P3 | SLA Met | 0
| SLA Not Met | 0
Closure Rate (P1 Bugs) |  | 75%
Closure Rate (P2 Bugs) |  | NA
Closure Rate (P3 Bugs) |  | NA